Event Planning Checklist

This checklist will help you get organized and stay well prepared for your bake sale. For additional details, please refer to CCF’s Bake for a Cure event page and  Guidebook to Planning a Big Heart Bake Sale. Additional planning, promotion, and decoration resources are available on the Bake for a Cure Resources page.

6 Weeks Ahead

- Visit CCF’s Bake for a Cure page for basic information and download the planning guidebook. Assemble your bake team and assign roles and responsibilities.

- Select a date for your bake sale.

- Find a high traffic location to hold your bake sale.

5 Weeks Ahead

- Visit CCF’s Bake for a Cure Resources page to view available materials and templates.

- Brainstorm with your team and determine the event theme, items to sell, and event activities.

- Consider selling beverages and other non-food items such as raffle tickets or donated gift baskets.

- Register your event with CCF (email: info@childrensardiomyopathy.org) to be listed on CCF’s community events page.

- Set-up a Go Fund Me page and Facebook fundraiser as a virtual bake sale option to expand your fundraising efforts.

- Reach out to local bakeries and grocery stores to request donations of baked goods and baking supplies.

- Reserve entertainment if including.

4 Weeks Ahead

- Inform your friends and family about your bake sale by sending emails and posting on social media using CCF’s sample text and social media (Facebook, Twitter) banners.

- Start hanging bake sale posters and distributing flyers around town.

- Promote your event to local magazines, newspapers, and community websites using CCF’s media guide and sample media alert.

- Order red CCF t-shirts and cure bands.

- Purchase stickers, packaging, and baking supplies.

2-3 Weeks Ahead

- Plan table set up and download decorate items from CCF’s Resources page.

- Determine which items can be made ahead of time and frozen.

- Continue to hang bake sale posters and distribute flyers around town.

- Send event reminders to friends and families.

- Recruit more volunteers and ask them to help spread the word.

1 Week Ahead

- Confirm your bake team and volunteer availability and event day responsibilities.

- Organize a bake day with your team to prepare your goodies.

- Package baked and donated items with cellophane bags and stickers and print labels from the CCF’s Resources page.

- Price your goodies in dollar amounts ($1-$5) to reduce the need for change.

- Print ingredient and/or pricing tent cards to display with your baked goods.

- Review CCF’s fact sheet so you are prepared to answer questions about pediatric cardiomyopathy.

Event Day

- Prepare a cash box with dollar bills for change.

- Give yourself and your team plenty of time to set up prior to the start of your sale.

- Set up a “calorie-free” donation jar.

- Ask your volunteers wear red and Bake for a Cure nametags.

- Talk to your customers and share facts on pediatric cardiomyopathy.

- Take photos and designate someone to post photos on social media while the bake sale is underway.

Post Event

- Thank everyone who helped with your bake sale and email event highlights and a few photos.

- Send CCF (email: info@childrenscardiomyopathy.org) a brief recap along with photos to add to our Bake for a Cure photo gallery.

- Send event proceeds via check (payable to “Children’s Cardiomyopathy Foundation”) to: Children’s Cardiomyopathy Foundation - Bake for a Cure, 24 West Railroad Avenue, Suite 408, Tenafly, NJ  07670.

- Congratulate yourself for a job well done! You have made an important difference in raising awareness of pediatric cardiomyopathy in your community.